# ANNUAL ACTION RESEARCH PLAN

## 1. Introduction

Action research is a reflective process that enables teachers to identify classroom challenges and implement strategies to improve teaching and learning. As a Research Coordinator, this annual action plan is designed to guide teachers through a systematic process of conducting action research within one academic year.

## 2. Objectives

- To promote a culture of reflective teaching and continuous professional development.

- To enhance teaching practices through evidence-based interventions.

- To improve student learning outcomes.

- To build teachers’ capacity in conducting action research.

## 3. Action Plan Timeline and Activities

### Phase 1: Orientation and Proposal Writing (January – February)

Activities: - Conduct orientation sessions on action research. - Share guidelines, formats, and sample proposals. - Assist teachers in identifying research problems. - Guide teachers in proposal writing.

Expected Output: - Draft action research proposals.

### Phase 2: Proposal Submission (April 28th)

Activities: - Submission of proposals by teachers. - Review of proposals by Research Coordinator/committee. - Provide feedback for improvement. - Final approval of proposals.

Expected Output: - Approved action research proposals.

### Phase 3: Intervention Planning (May onwards)

Activities: - Develop detailed intervention strategies. - Prepare data collection tools (questionnaires, observation checklists, tests). - Finalize implementation timeline.

Expected Output: - Completed intervention plan and research tools.

### Phase 4: Intervention Implementation and Data Collection (May – August)

Activities: - Implement intervention strategies in classrooms. - Monitor progress and provide continuous support. - Collect baseline, ongoing, and post-intervention data.

Expected Output: - Collected data and field records.

### Phase 5: Data Analysis and Report Writing (September – October)

Activities: - Analyze data using appropriate methods. - Interpret findings. - Prepare action research report.

Expected Output: - Draft action research report.

### Phase 6: Review and Finalization (November)

Activities: - Review and provide feedback on reports. - Edit and finalize reports. - Prepare presentation materials (PowerPoint/posters).

Expected Output: - Finalized reports and presentation materials.

### Phase 7: Action Research Seminar (December)

Activities: - Organize school-level action research seminar. - Teachers present their research findings. - Share best practices and reflections.

Expected Output: - Successful seminar and documented proceedings.

## 4. Monitoring and Support Mechanism

- Monthly progress meetings with teachers.

- Peer collaboration and support groups.

- Continuous guidance by the Research Coordinator.

## 5. Conclusion

This action plan provides a structured approach to conducting action research in the school. It ensures systematic implementation, monitoring, and sharing of findings to improve teaching practices and student learning outcomes.

Prepared by: Nim Dorji

Designation: Research and PD Coordinator

School: Tsenkharla Central School

Date: 20/3/2026